## Template
RISK ANALYSIS TABLE for Condo Care
Last Update: 2024 - 02 - 07
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
8 - Medium | Unauthorized access - direct crime related threat | - Weak Passwords that can be cracked by simple password cracking software and overuse of a single password are both vulnerabilities that can give life to unauthorized access threat | - People often reuse passwords because it is more convenient to memorize one password that unlocks all their accounts | Risk of account theft or data loss | 1 | 4 | Using a password management system like "LastPass"' | The importance of having strong password policies, strong authentication, and training stakeholders on security issues cannot be overstated. So the password validaiton doesn't accept weak passwords, and users are asked not to use previous passwords | 2 - Very low | -Stored passwords are encrypted. -Enforcing strong password policies that require complex passwords and regular changes. using password managers to help manage these securely. -Maintaining regular backups of all important data and store them in multiple, secure locations.
12 - High | Data leak | Weak end to end encryption and softaware vulnerabilities can cause data to be leaked | In many countries it is enforced by law that personal and financial data are stored in proper methods to prevent data leaks | Risk of account theft, and financial abuse | 3 | 4 | Using end to end encryption with public and private keys | Hiring a private company to help with data transfer | 2 - Very low | -using https -Train a some staffs members, especially those in financial roles, to recognize patterns and indicators of financial abuse. -Ensure that access to financial data and operations is strictly controlled based on roles, by limiting the number of people who can authorize transactions and access sensitive financial information.
9 - Medium | Hardware problems | Server is full or Maintenance scheduled | Slow software performance during maintenance |  | 3 | 3 | Upgrading server capacity, scheduling maintenance during non-peak hours, providing user notifications. |  | 3 - Very low | using lightweight database for easy hosting
9 - Medium | Interruption in Service Delivery | Software glitches, reliance on interconnected systems | Dependence on uninterrupted service for core operations, intricate software integrations. | Periodic service outages affecting user functionality. | 3 | 3 |  |  | 2 - Very low | hosted on well know server
2 - Very low | Corruption of the Data | when data input is not inaccurate, it becomes impossible to validate the data output | Not all humans are contientous about the data they handle | Risk of showing wrong results and skewing opinions in the wrong direction | 2 | 1 |  | Stakeholders need to be made aware of handling data properly. As well as constructing mechanisms that validate data during the input process as well as the output process | 2 - Very low
16 - High | SQL Injection | Web applications that do not sanitize user input, reliance on outdated or vulnerable database systems. | Use of web applications for processing sensitive transactions and storing personal customer data. | Unauthorized access to or manipulation of database content, leading to data breaches and system compromise. | 4 | 4 | Regular code reviews, use of web application firewalls (WAF), and implementation of secure coding practices. | Utilize prepared statements and parameterized queries, conduct vulnerability scanning and penetration testing. | 2 - Very low | -we have Implement a strong authentication mechanisms, such as multi-factor authentication (MFA), to ensure that only authorized users can access your database. -Isolate your database from the public internet and place it behind firewalls.
12 - High | DDoS Attack (Distributed Denial of Service Attack) | Network infrastructure that lacks redundancy, absence of a scalable DDoS protection solution. | Increasing reliance on online services for business operations and customer engagement. | Extended downtime of online services, loss of revenue, erosion of customer trust. | 3 | 4 | Contract with a DDoS mitigation service provider that offers scalable solutions to protect against large-scale attacks. | Strengthen network infrastructure, implement redundant pathways, and conduct regular stress testing. | 2 - Very low | -hosted server has protection. -Regularly backup all critical data and system. -Regularly test backups to ensure they can be restored quickly and effectively.
12 - High | Internal Security Risk | Over-privileged user accounts, inadequate user activity monitoring, and insufficient policy enforcement. | High-turnover environments and large numbers of contractors can increase the risk of insider threats. | Intellectual property theft, sabotage of IT systems, compliance violations. | 3 | 4 | Conduct thorough background checks, implement a policy of least privilege, and provide regular security awareness training. | Deploy advanced security monitoring tools to detect and respond to suspicious activities in real-time | 2 - Very low | -Enhance network security by using firewalls, intrusion detection and prevention systems and comprehensive endpoint protection to prevent unauthorized access and detect malicious activities. -Conduct regular security audits and continuous monitoring of IT systems to identify and respond to vulnerabilities or signs of sabotage. -Develop and regularly update an incident response plan that includes protocols for responding to and recovering from IT system sabotage.
20 - Critical | Ransomware Attack | Insufficient disaster recovery planning, inconsistent application of security updates and patches. | Use of diverse operating systems and applications increases the complexity of maintaining uniform security measures. | Disruption to business continuity, loss of sensitive data, financial impact due to ransom demands. | 4 | 5 | Maintain an updated disaster recovery and business continuity plan that includes ransomware scenarios. Simulate ransomware attacks to test the resilience of systems. | Regularly update and patch systems, enforce strict cybersecurity policies, and ensure that all data is backed up in a secure and segmented manner. | 2 - Very low | -Implement a robust backup system that includes frequent backups of all critical data. Store backups in multiple locations, including off-site and in cloud storage, to ensure data availability in case of an attack. -Regularly test your backups to ensure they are recoverable and effective in restoring business operations quickly
9 - Medium | Lost/Stolen Devices | Unencrypted data storage, lack of robust access controls, and insufficient employee training regarding physical device security. | The growing trend of remote work and the use of personal devices for work purposes increase the risk of devices being lost or stolen. | Exposure of corporate data, potential access by unauthorized individuals, legal and regulatory repercussions. | 3 | 3 | Implement and enforce mobile device management policies, including device tracking and remote wiping capabilities. | Mandate full-disk encryption for all company-owned devices, require strong authentication methods, and train employees in security best practices for device handling. | 2 - Very low | Accounts can be desactiveted remotely
12 - High
[11 empty] | Impact Level | Description
[11 empty] | 1 (Minor) | Minimal impact; slight inconveniences or small disruptions that do not significantly affect functionality.
[11 empty] | 2 (Negligible) | Insignificant impact; minor issues easily manageable with no significant risk to effective management.
[11 empty] | 3 (Moderate) | Moderate impact; disruptions or issues requiring attention but not severe enough to cause major problems.
[11 empty] | 4 (Severe) | Significant impact; major disruptions or problems requiring immediate attention to ensure smooth operation.
[11 empty] | 5 (Critical) | Catastrophic impact; severe consequences posing a significant threat to effective management, requiring urgent action.
[11 empty] | Likelihood Level | Description
[11 empty] | 1 (Rare) | Very low probability of occurrence; rare events that are unlikely to happen.
[11 empty] | 2 (Uncommon) | Low probability of occurrence; events that are infrequent but not unheard of.
[11 empty] | 3 (Moderate) | Moderate probability of occurrence; events that occur with some regularity but not frequently.
[11 empty] | 4 (Likely) | High probability of occurrence; events that have a significant chance of happening.
[11 empty] | 5 (Highly Likely) | Very high probability of occurrence; events that are expected to happen frequently.