## REQUIREMENT MATRIX
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: | Hassan Moharram |  |  | PROJECT ID: | AX-EMEA-000302
PROJECT SPONSOR: | Concordia |  |  | PROJECT TITLE: | CondoCare
REQUIREMENT INFORMATION |  |  |  |  | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | SOURCE | BUSINESS OBJECTIVE | DELIVERABLE(S | VERFICATION | VALIDATION
US001 | Mandatory | User Registration | High | Requirements Doc | As a public user, I want to create a profile with a unique username, contact email, and phone number, and upload a profile picture. As a user, I want to provide a registration key obtained from the condo management company to complete the registration process. | Registration system | User is able to register and login | Unit test
US002 | Mandatory | Property Profile Creation | High | Requirements Doc | As a condo management company, I want to create a profile for each property under my management, specifying details such as property name, unit count, parking count, locker count, and address. | Dynamic website with the ablility to create property profile | Functional property page | Unit test.
US003 | Mandatory | File Upload and Sharing |  | Requirements Doc | As a condo management company, I want to upload and share important condo files for each property, such as declarations, budgets, and meeting minutes. As a condo owner, I want to access and view shared condo files for my respective property. | Upload system | User is able to upload documents | Unit test.
US004 |  | Detailed Unit, Parking, and Locker Information |  | Requirements Doc | As a condo management company, I want to enter detailed information for each condo unit, parking spot, and locker, including unit id, size, owner information, occupant details, and associated condo fees. | Database-frontend connections and exposure of API | User is able to see all details about their unit/property | Unit test.
US005 |  | Financial System |  | Requirements Doc | As a condo management company, I want to set condo fees per square foot and per parking spot in the financial system. As a condo owner, I want to view and understand the calculated condo fees and access annual financial reports. | Full financial system with fee calculation | user is able to see all financial information and report | Unit test.
US006 |  | Reservation System |  | Requirements Doc | As a condo management company, I want to set up common facilities requiring reservations. As a user, I want to reserve facilities through a calendar-like interface, with visibility into availability and a first-come-first-serve basis. | Reservation system for facilities | User is able to reserve facilities | Unit test.
US007 |  | Request Submission and Assignment |  | Requirements Doc | As a condo owner, I want to submit requests (e.g., moving in/out, intercom changes) and track their status. As an employee, I want to receive and manage requests based on their type and assign them to the appropriate personnel. | Request system | user is able to submit and see requests, admin is able to resolve requests | Unit test.
US008 |  | User Roles Management |  | Requirements Doc | As a condo management company, I want to set up different roles (e.g., managers, finance personnel) for employees responsible for the same property. | User Roles Management | users are separated by roles | Unit test & Integration test
US009 |  | Forum |  | Requirements Doc | As a user, I want to post and reply to discussions related to my property in the forum. | Forum system with chat | users able to join chat rooms | Unit test.
US10 |  | Events Management |  | Requirements Doc | As a user, I want to organize events and invite other occupants to attend and be able to accept event invitations. | Events system | users are able to create events | Unit test.
US12 |  | Notifications |  | Requirements Doc | As a user I want to be able to view new notifications and automatically notify me if there are any updates. | Websocket connections | user is able to establish a websocket connection for real time data | Unit test.