## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| SUser registration |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
|  |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Website and mobile application with all required documentation
| CondoCare | Hassan Moharram | 15/1/24 | 2024-05-01 |  | 15% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
| User registration | User Stories | Shivam | 4 | 2024-03-02 | 2024-06-02 | 3 | Complete | React webstite + react native moblile for IOS and Android complete
Sprint 2
| Discussion Forum | User Stories |  | 6 |  |  |  | Not Started
| Property Registration | User Stories |  | 6 |  |  |  | Not Started
| Unit, locker, and Parking details | User Stories |  | 6 |  |  |  | Not Started
Sprint 3
| Reservation system | User Stories |  | 8 |  |  |  | Not Started
| User roles management | User Stories |  | 7 |  |  |  | Not Started
Sprint 4
| Request Submission and Assignment | User Stories |  | 7 |  |  |  | Not Started
| Events Management | User Stories |  | 6 |  |  |  | Not Started
| Discounts and Offers | User Stories |  | 3 |  |  |  | Not Started

## -Disclaimer-
Please update this as per your ERP system name and policies you want to adopt