## Template
RISK ANALYSIS TABLE for Condo Care
Last Update: 2024 - 02 - 07
Ranking | Threats (1) | Vulnerabilities (2) | Contextual factors | Risks (3) | Likelihood from 1 to 5 | Impact from 1 to 5 | Reduction of Threats (Acceptance Strategy) | Reduction of Vulnerabilities (Protection Strategy) | Level of residual Risk
12 - High | Unauthorized access - direct crime related threat | - Weak Passwords that can be cracked by simple password cracking software and overuse of a single password are both vulnerabilities that can give life to unauthorized access threat | - People often reuse passwords because it is more convenient to memorize one password that unlocks all their accounts | Risk of account theft or data loss | 4 | 4 | Using a password management system like "LastPass"' | The importance of having strong password policies, strong authentication, and training stakeholders on security issues cannot be overstated. So the password validaiton doesn't accept weak passwords, and users are asked not to use previous passwords | 2 - Very low
20 - Critical | Data leak | Weak end to end encryption and softaware vulnerabilities can cause data to be leaked | In many countries it is enforced by law that personal and financial data are stored in proper methods to prevent data leaks | Risk of account theft, and financial abuse | 3 | 4 | Using end to end encryption with public and private keys | Hiring a private company to help with data transfer | 4 - Low
2 - Very low | Hardware problems | Server is full or Maintenance scheduled | Slow software performance during maintenance |  | 3 | 3 | Upgrading server capacity, scheduling maintenance during non-peak hours, providing user notifications. |  | 2 - Very low
8 - Medium | Interruption in Service Delivery | Software glitches, reliance on interconnected systems | Dependence on uninterrupted service for core operations, intricate software integrations. | Periodic service outages affecting user functionality. | 3 | 3 |  |  | 2 - Very low
12 - High | Corruption of the Data | when data input is not inaccurate, it becomes impossible to validate the data output | Not all humans are contientous about the data they handle | Risk of showing wrong results and skewing opinions in the wrong direction | 2 | 1 |  | Stakeholders need to be made aware of handling data properly. As well as constructing mechanisms that validate data during the input process as well as the output process | 2 - Very low
CONFIDENTIAL