## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Website and mobile application with all required documentation
| CondoCare | Hassan Moharram | 15/1/24 | 2024-05-01 |  | 15% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
| User registration | User Stories | Shivam | 4 | 2024-03-02 | 2024-06-02 | 3 | Complete | React webstite + react native moblile for IOS and Android complete
Sprint 2
| Database creation | Enhancement | Shivam |  | 15/2/24 | 18/2/24 | 3 | Complete
| Backend endpoints | Enhancement | Shivam |  | 18/2/24 | 21/2/24 | 3 | Complete
| Landing page (Owners) | Enhancement | Omar |  | 21/2/24 | 25/2/24 | 4 | Complete
| Landing page (Renters) | Enhancement | Aly |  | 27/2/24 | 29/2/24 | 3 | Complete
| Discussion Forum | User Stories | Jackson | 6 | 24/2/24 | 26/2/24 | 2 | Complete
| Discussion Forum frontend | Sub user story | Jackson |  | 27/2/24 | 29/2/24 | 3 | Complete
| Dicussion forum backend | Sub user story | Shivam |  | 18/2/24 | 21/2/24 | 3 | Complete
| Property list page | Sub user story | Hassan |  | 22/2/24 | 25/2/24 | 3 | Complete
| Condo list | Sub user story | Hassan |  | 22/2/24 | 25/2/24 | 3 | Complete
| Property view | Sub user story | Dimitri | 3 | 19/2/24 | 26/2/24 | 7 | Complete
| Property Registration backend | User Stories | Shivam | 6 | 18/2/24 | 21/2/24 | 3 | Complete
| Property Registration Frontend | Sub user story | Kaothar |  | 22/2/24 | 27/2/24 | 5 | Complete
| inbox / notification on post replies and requests | Sub user story | Vraj |  | 22/2/24 | 27/2/24 | 5 | Complete
| Unit, locker, and Parking details | User Stories | Shivam | 6 | 18/2/24 | 21/2/24 | 3 | Complete
Sprint 3
| Request system | User Stories | Hassan | 8 | 29/2/24 | 19/3/24 | 10 | Complete
| Requests endpoints | Sub user story | Hassan | 2024-03-08 | 29/2/24 | 2024-01-03 | 2 | Complete
| Request submitter form | Sub user story | Vraj | 2024-03-08 | 2024-01-03 | 2024-03-03 | 2 | Complete
| Request list view (employee) | Sub user story | Vraj | 2024-02-08 | 2024-01-02 | 2024-03-03 | 2 | Complete
| Database web-socket connection for notification | Enhancement | Shivam |  | 2024-01-03 | 2024-10-03 | 9 | Complete
| Add new role: Owner/Renter | Enhancement | Kaothar |  | 2024-01-03 | 2024-03-03 | 2 | Complete
| Navigation/Routing | Enhancement | Dimitri |  | 2024-02-03 | 2024-11-03 | 9 | Complete
| User roles management (testing) | User Stories | Shivam | 7 | 2024-02-03 | 2024-10-03 | 8 | Complete
| Landing Page | Enhancement | Aly |  | 19/3/24 | 21/3/24 | 3 | Complete
| Dashboard | Enhancement | Kaothar |  | 19/3/24 | 21/3/24 | 3 | Complete
| Admin role tests | Sub user story | Omar | 2024-03-07 | 2024-04-03 | 15/3/24 | 11 | Complete
| Public user tests | Sub user story | Jackson | 2024-02-07 | 2024-02-03 | 15/3/24 | 13 | Complete
| Employee tests | Sub user story | Aly | 2024-02-07 | 2024-02-02 | 15/3/24 | 13 | Complete
Sprint 4
Front end
| Reservation System | User Stories | Aly | 2024-04-08 | 23/3 | 2024-01-04 |  | Not Started
| Calendar | Sub user story | Kaothar | 2024-02-08 | 23/3 | 30/3 |  | Not Started
| List of facilities per property | Sub user story | Vraj | 2024-01-08 | 23/3 | 29/3 |  | Not Started
| Events Management | User Stories | Aly | 2024-04-06 | 23/3 | 30/3 |  | Not Started
| Events Submission | Sub user story | Kaothar | 2024-02-06 | 23/3 | 30/3 |  | Not Started
| Upcoming events (in dashboard) | Sub user story | Dimitri | 2024-01-06 | 23/3 | 30/3 |  | Not Started
| Events view (admin) | Sub user story | Aly | 2024-01-06 | 23/3 | 30/3 |  | Not Started
| Dashboard for admin | Enhancement | Jackson |  | 23/3 | 30/3 |  | Not Started
Backend
| Reservation System US006 | User Stories | Shivam | 2024-04-08 | 23/3 | 30/3 |  | Not Started
| Add facilities to database | Sub user story | Shivam | 2024-02-08 | 23/3 | 30/3 |  | Not Started
| Reservation System endpoints | Sub user story | Hassan | 2024-01-08 | 23/3 | 30/3 |  | Not Started
| Reservation system logic | Sub user story | Dimitri | 2024-01-08 | 23/3 | 30/3 |  | Not Started
| Events Management US010 | User Stories | Shivam | 2024-02-06 | 23/3 | 30/3 |  | Not Started
| Events endpoints | Sub user story | Hassan | 2024-01-06 | 23/3 | 30/3 |  | Not Started
| Events logic | Sub user story | Shivam | 2024-01-06 | 23/3 | 30/3 |  | Not Started

## -Disclaimer-
Please update this as per your ERP system name and policies you want to adopt